MyDas, Progress Report January 2018.

A main activity has been to set up a github repository https://github.com/laurieKell/mydas along with a wiki https://github.com/laurieKell/mydas/wiki

Work has progressed on each of the tasks and is being documented on the wiki, code is being developed using the github repository, generic methods are being added to FLR www.github.com/FLR and the relevant packages will be released via www.flr-project.org. All methods are being documentation including vignettes https://github.com/laurieKell/mydas/wiki/vignettes, shiny-apps being developed for dissemination https://github.com/laurieKell/mydas/wiki/6-Liaison-with-Marine-Institute and a variety of peer review papers being drafted https://github.com/laurieKell/mydas/wiki/Outputs A database for raw data and MSE results has been developed https://github.com/laurieKell/mydas/wiki/2-Data-collation
### Task 1
- The initial species and stocks of interest have been identified and work is starting on categorising stocks under the 6 ICES data quality categories (https://github.com/laurieKell/mydas/wiki/1-Stock-prioritisation).
- It is proposed that the final choice of stocks be made at the April meeting after consultation with MI.
### Task 2
- Examples of the different datasets (I.e. commercial, survey, life history, assessment and economic)have been collated (https://github.com/laurieKell/mydas/wiki/2-Data-Collation) and are now being summarised by species, stock, fleet and fishery.
- R Markdown documents with analysis available on https://github.com/laurieKell/mydas/tree/master/tasks
### Task 3
- mpb Prototype of MSE framework using life histories available see examples in https://github.com/laurieKell/mydas/tree/master/vignettes/FLife
- Example OM conditioned on life history parameters, written up as a vignette and added to the mpb FLR pacakge, see https://github.com/laurieKell/mydas/tree/master/vignettes/mse
- Generic OEM https://github.com/laurieKell/mydas/tree/master/vignettes/oem
### Task 4
A summary of all the data poor methods available worldwide has been made in a google spreadsheet https://docs.google.com/spreadsheets/d/17_qQdzDY41ZrL0yT6QtHpUR4_ydxx_xfCh4GiDqYymU/edit?usp=sharing
### Task 5
Ongoing , once the stocks and candidate methods are identified under task 1 and 4, they will be simulation tested using the framework developed in task 3.
## Papers
Still to agree see https://github.com/laurieKell/mydas/wiki/Outputs
A set of paper outlines have been drafted and are on openleaf and code will be placed on https://github.com/laurieKell/mydas/tree/master/papers as developed.